## Instructions
Assessment Task: AI Manpower Allocation & Project Scheduling
1. Objective
Design and develop a scalable, AI-enabled manpower allocation and project scheduling solution that can:
Manage employees/resources
Manage projects
Manage stages/activities
Allocate manpower to projects
Calculate schedules based on dates and working calendars
Identify manpower shortages
Identify employee allocation conflicts
Consider employee designation/skills when allocating
Provide scheduling and reporting output
Implement AI-assisted recommendations where appropriate
2. Before You Start: Understand the Business Requirement
1. Review all sheets provided in this Excel file before starting development.
2. Understand the relationship between the Master data and the Expected Output.
3. The sample data is provided only to explain the business scenario and expected outcome — do not assume it represents final production volume.
4. Your solution must support unlimited additional employees, projects, companies, stages, designations, vendors, documents, and transactions in the future. Do not hardcode against the sample size.
3. Sheet Guide
Stage–Designation Master: The 8 production stages, valid designations per stage, and calendar rules (White Collar / Blue Collar).
Employee Master (Sample): 53 sample employees across all stages. System must allow adding/editing/removing employees beyond this sample.
Project Master (Sample): 7 sample projects with planned stage durations. System must allow adding new projects.
Calendar Rules: Working days, weekly off, and overtime logic used for allocation and scheduling calculations.
Expected Output: Sample manpower allocation view for project PRJ007 "VILLA A12 – Renovation" (planned over 60 calendar days). This is a reference for the required output format.
4. Key Business Rules
White Collar staff (Design, Planning, Procurement, Sourcing, QA/Management):
Work Monday–Friday
Saturday & Sunday = Week Off
No overtime
Blue Collar staff (Manufacturing, QC Inspection, Packing, Shipping/Dispatch):
Work Monday–Saturday
Sunday = Week Off
Overtime allowed beyond standard 8 hrs/day, or as approved
An employee can only be allocated to a project stage that matches their designation (see Stage–Designation Master).
Standard shift = 8 hours/day. Blue Collar overtime is tracked separately at OT rate.
Employee IDs, Project IDs, and all data in this workbook are sample/illustrative — the system must support unlimited additions, not just this sample set.
(Days) columns in the Project Master represent calendar days for that stage (stage start date to stage end date). These are NOT a count of working days — actual working days will be fewer once each employee category's weekly-off is excluded. This matches how the Expected Output sample is built.
5. Deliverable
Using the supplied sample data and business rules as a reference, design and develop a scalable, AI-enabled manpower allocation and project scheduling solution with a proper, well-structured architecture covering the data layer, allocation logic, scheduling engine, validation/conflict checks, AI recommendations, and reporting output.

## Stage-Designation Master
Stage No. | Production Stage | Designation / Role | Category | Work Days | Weekly Off | Standard Shift (Hrs) | Overtime Applicable | Production Stage
1 | Design | Design Manager | White Collar | Mon–Fri | Sat, Sun | 8 | No | Design
1 | Design | Design Engineer | White Collar | Mon–Fri | Sat, Sun | 8 | No | Design
1 | Design | CAD Draftsman | White Collar | Mon–Fri | Sat, Sun | 8 | No | Design
2 | Planning | Planning Manager | White Collar | Mon–Fri | Sat, Sun | 8 | No | Planning
2 | Planning | Project Planner / Scheduler | White Collar | Mon–Fri | Sat, Sun | 8 | No | Planning
3 | Procurement | Procurement Manager | White Collar | Mon–Fri | Sat, Sun | 8 | No | Procurement
3 | Procurement | Procurement Officer | White Collar | Mon–Fri | Sat, Sun | 8 | No | Procurement
4 | Sourcing | Sourcing Manager | White Collar | Mon–Fri | Sat, Sun | 8 | No | Sourcing
4 | Sourcing | Vendor Development Executive | White Collar | Mon–Fri | Sat, Sun | 8 | No | Sourcing
5 | Manufacturing | Production Supervisor | Blue Collar | Mon–Sat | Sun | 8 | Yes | Manufacturing
5 | Manufacturing | Carpenter | Blue Collar | Mon–Sat | Sun | 8 | Yes | Manufacturing
5 | Manufacturing | Machine Operator (CNC/Edge Band) | Blue Collar | Mon–Sat | Sun | 8 | Yes | Manufacturing
5 | Manufacturing | Welder / Fabricator | Blue Collar | Mon–Sat | Sun | 8 | Yes | Manufacturing
5 | Manufacturing | Finishing / Polishing Technician | Blue Collar | Mon–Sat | Sun | 8 | Yes | Manufacturing
5 | Manufacturing | Helper / Assistant | Blue Collar | Mon–Sat | Sun | 8 | Yes | Manufacturing
6 | Quality Control | QA Engineer | White Collar | Mon–Fri | Sat, Sun | 8 | No | Quality Control
6 | Quality Control | QC Inspector | Blue Collar | Mon–Sat | Sun | 8 | Yes | Quality Control
7 | Packing | Packing Supervisor | Blue Collar | Mon–Sat | Sun | 8 | Yes | Packing
7 | Packing | Packing Helper | Blue Collar | Mon–Sat | Sun | 8 | Yes | Packing
8 | Shipping | Logistics Coordinator | White Collar | Mon–Fri | Sat, Sun | 8 | No | Shipping
8 | Shipping | Dispatch Executive | Blue Collar | Mon–Sat | Sun | 8 | Yes | Shipping
8 | Shipping | Driver | Blue Collar | Mon–Sat | Sun | 8 | Yes | Shipping

## Employee Master (Sample)
Employee ID | Employee Name | Designation | Stage | Category | Work Days | Weekly Off | OT Eligible | Skill Level | Date of Joining | Status
EMP001 | Ahmed Khan | Design Manager | Design | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2022-03-15 | Active
EMP002 | Ahmed Sharma | Design Engineer | Design | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2023-05-10 | Active
EMP003 | Ahmed Patel | Design Engineer | Design | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2023-01-20 | Active
EMP004 | Ahmed Malik | Design Engineer | Design | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2022-03-15 | Active
EMP005 | Ahmed Iyer | CAD Draftsman | Design | White Collar | Mon–Fri | Sat, Sun | No | Senior | 2025-06-20 | Active
EMP006 | Ahmed Hussain | CAD Draftsman | Design | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2022-01-10 | Active
EMP007 | Ahmed Reddy | CAD Draftsman | Design | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2022-03-15 | Active
EMP008 | Ahmed Ansari | Planning Manager | Planning | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2023-01-20 | Active
EMP009 | Ahmed Nair | Project Planner / Scheduler | Planning | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2025-01-15 | Active
EMP010 | Ahmed Siddiqui | Project Planner / Scheduler | Planning | White Collar | Mon–Fri | Sat, Sun | No | Senior | 2025-01-15 | Active
EMP011 | Ahmed Verma | Procurement Manager | Procurement | White Collar | Mon–Fri | Sat, Sun | No | Senior | 2023-01-20 | Active
EMP012 | Ahmed Baig | Procurement Officer | Procurement | White Collar | Mon–Fri | Sat, Sun | No | Senior | 2025-06-20 | Active
EMP013 | Ahmed Menon | Procurement Officer | Procurement | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2022-01-10 | Active
EMP014 | Ahmed Qureshi | Sourcing Manager | Sourcing | White Collar | Mon–Fri | Sat, Sun | No | Senior | 2024-02-14 | Active
EMP015 | Ahmed Rao | Vendor Development Executive | Sourcing | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2023-05-10 | Active
EMP016 | Ahmed Farooqi | Vendor Development Executive | Sourcing | White Collar | Mon–Fri | Sat, Sun | No | Senior | 2023-01-20 | Active
EMP017 | Ahmed Pillai | Production Supervisor | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2022-03-15 | Active
EMP018 | Ahmed Shaikh | Production Supervisor | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2024-02-14 | Active
EMP019 | Ahmed Gupta | Production Supervisor | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2023-09-01 | Active
EMP020 | Ahmed Chaudhry | Carpenter | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2025-06-20 | Active
EMP021 | Rahul Khan | Carpenter | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2022-01-10 | Active
EMP022 | Rahul Sharma | Carpenter | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2024-07-01 | Active
EMP023 | Rahul Patel | Carpenter | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2022-03-15 | Active
EMP024 | Rahul Malik | Carpenter | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2022-03-15 | Active
EMP025 | Rahul Iyer | Carpenter | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2023-05-10 | Active
EMP026 | Rahul Hussain | Machine Operator (CNC/Edge Band) | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2025-06-20 | Active
EMP027 | Rahul Reddy | Machine Operator (CNC/Edge Band) | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2025-06-20 | Active
EMP028 | Rahul Ansari | Machine Operator (CNC/Edge Band) | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2022-03-15 | Active
EMP029 | Rahul Nair | Machine Operator (CNC/Edge Band) | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2023-01-20 | Active
EMP030 | Rahul Siddiqui | Welder / Fabricator | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2022-03-15 | Active
EMP031 | Rahul Verma | Welder / Fabricator | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2022-03-15 | Active
EMP032 | Rahul Baig | Welder / Fabricator | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2023-05-10 | Active
EMP033 | Rahul Menon | Finishing / Polishing Technician | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2023-09-01 | Active
EMP034 | Rahul Qureshi | Finishing / Polishing Technician | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2023-09-01 | Active
EMP035 | Rahul Rao | Finishing / Polishing Technician | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2023-01-20 | Active
EMP036 | Rahul Farooqi | Helper / Assistant | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2023-05-10 | Active
EMP037 | Rahul Pillai | Helper / Assistant | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2022-03-15 | Active
EMP038 | Rahul Shaikh | Helper / Assistant | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2022-06-01 | Active
EMP039 | Rahul Gupta | Helper / Assistant | Manufacturing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2023-01-20 | Active
EMP040 | Rahul Chaudhry | QA Engineer | Quality Control | White Collar | Mon–Fri | Sat, Sun | No | Senior | 2024-07-01 | Active
EMP041 | Suresh Khan | QA Engineer | Quality Control | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2023-05-10 | Active
EMP042 | Suresh Sharma | QC Inspector | Quality Control | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2023-09-01 | Active
EMP043 | Suresh Patel | QC Inspector | Quality Control | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2023-01-20 | Active
EMP044 | Suresh Malik | QC Inspector | Quality Control | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2023-09-01 | Active
EMP045 | Suresh Iyer | Packing Supervisor | Packing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2023-05-10 | Active
EMP046 | Suresh Hussain | Packing Helper | Packing | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2023-01-20 | Active
EMP047 | Suresh Reddy | Packing Helper | Packing | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2023-09-01 | Active
EMP048 | Suresh Ansari | Packing Helper | Packing | Blue Collar | Mon–Sat | Sun | Yes | Mid | 2024-07-01 | Active
EMP049 | Suresh Nair | Logistics Coordinator | Shipping | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2024-07-01 | Active
EMP050 | Suresh Siddiqui | Dispatch Executive | Shipping | Blue Collar | Mon–Sat | Sun | Yes | Junior | 2023-05-10 | Active
EMP051 | Suresh Verma | Dispatch Executive | Shipping | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2023-01-20 | Active
EMP052 | Suresh Baig | Driver | Shipping | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2025-01-15 | Active
EMP053 | Suresh Menon | Driver | Shipping | Blue Collar | Mon–Sat | Sun | Yes | Senior | 2023-05-10 | Active
EMP054 | Syed Hussain | Project Manager | Manager | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2024-07-01 | Active
EMP055 | Tyson | Project Manager | Manager | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2024-09-01 | Active
EMP056 | Vinay | Project Manager | Manager | White Collar | Mon–Fri | Sat, Sun | No | Mid | 2025-02-01 | Active

## Project Master (Sample)
PRODUCTION STAGES
Project ID | Project Name | Client / Site | Project Manager | Location | Priority | Start Date | Target End Date | Design (Calendar Days) | Planning (Calendar Days) | Procurement (Calendar Days) | Sourcing (Calendar Days) | Manufacturing (Calendar Days) | Quality Control (Calendar Days) | Packing (Calendar Days) | Shipping (Calendar Days) | Status
PRJ001 | Al Barari Villa – Interior Joinery | Private Villa Client | Syed Hussain | Al Barari, Dubai | High | 2026-09-01 | 2026-11-10 | 7 | 5 | 6 | 4 | 25 | 5 | 3 | 4 | Planned
PRJ002 | Palm Jumeirah Hotel – Joinery & MEP Fit-out | Hospitality Group | Tyson | Palm Jumeirah, Dubai | High | 2026-09-15 | 2026-12-20 | 10 | 7 | 8 | 5 | 40 | 7 | 5 | 6 | Planned
PRJ003 | Business Bay Office – Joinery & Manufacturing | Corporate Client | Syed Hussain | Business Bay, Dubai | Medium | 2026-10-01 | 2026-11-25 | 5 | 4 | 5 | 3 | 18 | 4 | 3 | 3 | Planned
PRJ004 | Dubai Mall Retail Store – Fast-track Fit-out | Retail Brand | Vinay | Downtown Dubai | Urgent | 2026-09-20 | 2026-10-25 | 3 | 2 | 3 | 2 | 14 | 3 | 2 | 2 | Planned
PRJ005 | Sharjah Mosque – Furniture Manufacturing | Government / Waqf | Tyson | Sharjah | Medium | 2026-10-05 | 2026-12-05 | 6 | 5 | 6 | 4 | 22 | 5 | 4 | 5 | Planned
PRJ006 | Dubai Marina Yacht – Interior Joinery | Private Owner | Syed Hussain | Dubai Marina | High | 2026-10-12 | 2026-12-30 | 8 | 6 | 7 | 5 | 30 | 6 | 4 | 5 | Planned
PRJ007 | ABC RENOVATION PROJECT | Private Owner | Syed Hussain | Palm Jumeirah, Dubai | High | 01-Sep-2026 | 0 | 5 | 5 | 5 | 3 | 48 | 2 | 3 | 3 | Planned

## Calendar Rules
Category | Work Days | Weekly Off Day(s) | Standard Daily Hours | Overtime Rule | Notes
White Collar | Monday – Friday | Saturday, Sunday | 8 | Not Applicable | Design, Planning, Procurement, Sourcing, QA Engineer, Logistics Coordinator and other management/engineering roles.
Blue Collar | Monday – Saturday | Sunday | 8 | Applicable beyond 8 hrs/day or on approved additional working days (incl. Sunday if approved) | Manufacturing, QC Inspector, Packing, Dispatch/Driver and other operational/production floor roles.
Public Holiday | As per UAE official calendar | - | - | Applicable if worked, per labor law | Candidate's system should allow admin to mark specific dates as Public Holidays affecting all categories.

## Expected Output
Project : PRJ007 - ABC RENOVATION PROJECT, Production Manpower Plan (Sample Expected Output)
| Project : PRJ007 - ABC RENOVATION PROJECT, Production Manpower Plan (Sample Expected Output) | Resource | Duration | Start | End | Sep 2026 | [29 empty] | Oct 2026
Ref | Tasks | Role & Employee | Days | Date | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[6 empty] | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA | SU | M | T | W | T | F | SA
| Stage 1: Design | Design Team (White Collar) | 5 | 01-Sep-2026 | 04-Sep-2026 | T: Design
1 | Concept design & drawings | Design Engineer - Ahmed Sharma (EMP002) | 3 | 01-Sep-2026 | 03-Sep-2026 | T: 1; W: 2; T: 3
2 | CAD detailing & shop drawings | CAD Draftsman - Ahmed Iyer (EMP005) | 2 | 03-Sep-2026 | 04-Sep-2026 | T: 4; F: 5
| Stage 2: Planning | Planning Team (White Collar) | 5 | 2026-09-07 | 2026-09-11 | M: Planning
3 | Production planning & scheduling | Project Planner - Ahmed Nair (EMP009) | 5 | 07-Sep-2026 | 2026-09-11 | M: 6; T: 7; W: 8; T: 9; F: 10
| Stage 3: Procurement | Procurement Team (White Collar) | 5 | 14-Sep-2026 | 18-Sep-2026 | M: Procurement
4 | Material & BOQ procurement | Procurement Officer - Ahmed Baig (EMP012) | 5 | 13-Sep-2026 | 18-Sep-2026 | M: 11; T: 12; W: 13; T: 14; F: 15
| Stage 4: Sourcing | Sourcing Team (White Collar) | 3 | 21-Sep-2026 | 24-Sep-2026 | M: Sourcing
5 | Vendor & supplier sourcing | Vendor Dev. Exec. - Ahmed Rao (EMP015) | 3 | 21-Sep-2026 | 24-Sep-2026 | M: 16; T: 17; W: 18
| Stage 5: Manufacturing | Production Floor (Blue Collar) | 48 | 19-Sep-2026 | 23-Sep-2026 | T: Manufacturing
6 | Carpentry & assembly | Carpenter - Rahul Sharma (EMP022) | 15 | 24-Sep-2026 | 2026-10-10 | T: 19; F: 20; SA: 21; M: 22; T: 23; W: 24; T: 25; F: 26; SA: 27; M: 28; T: 29; W: 30; T: 31; F: 32; SA: 33
7 | CNC cutting & edge banding | Machine Operator - Rahul Hussain (EMP026) | 10 | 24-Sep-2026 | 2026-10-05 | T: 19; F: 20; SA: 21; M: 22; T: 23; W: 24; T: 25; F: 26; SA: 27; M: 28
8 | Welding & metal fabrication | Welder/Fabricator - Rahul Siddiqui (EMP030) | 11 | 06-Oct-2026 | 18-Oct-2026 | T: 29; W: 30; T: 31; F: 32; SA: 33; M: 34; T: 35; W: 36; T: 37; F: 38; SA: 39
9 | Finishing & polishing | Finishing Technician - Rahul Menon (EMP033) | 12 | 11-Oct-2026 | 23-Oct-2026 | M: 34; T: 35; W: 36; T: 37; F: 38; SA: 39; M: 40; T: 41; W: 42; T: 43; F: 44; SA: 45
| Stage 6: Quality Control | QA/QC Team (Mixed) | 2 | 24-Oct-2026 | 26-Oct-2026 | SA: QA/QC
10 | In-line quality inspection | QC Inspector - Suresh Sharma (EMP042) | 1 | 24-Oct-2026 | 24-Oct-2026 | SA: 45
11 | Final QA sign-off | QA Engineer - Rahul Chaudhry (EMP040) | 1 | 26-Oct-2026 | 26-Oct-2026 | M: 46
| Stage 7: Packing | Packing Team (Blue Collar) | 3 | 26-Oct-2026 | 28-Oct-2026 | M: Packing
12 | Packing & crating | Packing Helper - Suresh Hussain (EMP046) | 3 | 26-Oct-2026 | 28-Oct-2026 | M: 46; T: 47; W: 48
| Stage 8: Shipping | Logistics Team (Mixed) | 3 | 29-Oct-2026 | 30-Oct-2026 | T: Shipping
13 | Dispatch coordination | Logistics Coordinator - Suresh Nair (EMP049) | 1 | 29-Oct-2026 | 29-Oct-2026 | T: 49
14 | Loading & transport | Driver - Suresh Baig (EMP052) | 2 | 30-Oct-2026 | 2026-10-31 | F: 50; SA: 51
Total (Resource-Days, sum of all employees' individual days)
Report Summary
PROJECT NAME | PRJ007 - ABC RENOVATION PROJECT
PROJECT MANAGER | Syed Hussain
Total Man Power Days | 74 | Days
Actual Working Days | 51 | Days
Project Start Date | 01-Sep-2026
Project Expected Completion Date | 2026-10-31
Manufacturing Stages
SNO | Stage Name | Days
1 | Design | 5
2 | Planning | 5
3 | Procurement | 5
4 | Sourcing | 3
5 | Manufacturing | 48
6 | Quality Control | 2
7 | Packing | 3
8 | Shipping | 3